## Simple Safety Risk Register
SIMPLE SAFETY RISK REGISTER
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | RISK LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | (IMPACT X PROBABILITY) Address the highest first | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
Load Shedding | Power failuers can shut down servers, networking equipment and office operations | 4 | 5 | 20 | Critical | Install UPS systems and backup generators to maintain power during outages. | Priya Singh - Network & Infrastructure Administrator | 1
UPS or generator failure | Backup power systems may fail during extender outages | 4 | 2 | 8 | Medium | Perform regular maintenance and testing of backup power systems. | Priya Singh - Network & Infrastructure Administrator | 2
Server hardware failure | Hard drive crashes or server malfunction could cause systems downtime | 5 | 3 | 15 | High | Use redundant servers and schedule regular hardware monitoring. | Priya Singh - Network & Infrastructure Administrator | 3
Cooling system failure | Server rooms overheating can damage hardware | 4 | 2 | 8 | Medium | Install temperature monitoring and backup cooling systems in server rooms. | Michael Jacobs - IoT Systems Engineer | 4
Single internet connection | If the primary fibre connection fails, the business could lose connectivity | 4 | 4 | 16 | Critical | Implement a secondary ISP connection for redundancy. | Priya Singh - Network & Infrastructure Administrator | 5
Router or firewall failure | A failed router or firewall could disconnect the entire company network | 4 | 3 | 12 | High | Deploy redundant networking equipment and maintain backup configurations. | Priya Singh - Network & Infrastructure Administrator
Poor network segmentation | If internal networks are not separated, an attack could spread easily | 4 | 3 | 12 | High | Segment networks using VLANs and access control policies. | Kabelo Dlamini - Cybersecurity Specialist
Misconfigured network devices | Incorrect settings could expose internal systems to the internet | 3 | 3 | 9 | Medium | Perform regular configuration audits and security reviews. | Priya Singh - Network & Infrastructure Administrator
Ransomware attacks | Malware could encrypt company servers and customer data | 5 | 3 | 15 | High | Implement endpoint protection and maintain secure offline backups. | Kabelo Dlamini - Cybersecurity Specialist
Weak passwords | Simple or reuses passwords increase the risk of unauthorized access | 4 | 4 | 16 | Critical | Enforce strong password policies and multi-factor authentication (MFA). | Kabelo Dlamini - Cybersecurity Specialist
Unpatched software | Outdates systems may contain exploitable security flaws | 4 | 4 | 16 | Critical | Apply regular security updates and patch management procedures. | Lerato Mokoena - Chief Technology Officer
Phishing attacks | Employees may accidentally give away login credentials | 3 | 4 | 12 | High | Conduct employee cybersecurity awareness and phishing training. | Kabelo Dlamini - Cybersecurity Specialist
Data corruption | Software bugs or system crashes could damage data | 4 | 3 | 12 | High | Implement automated data integrity checks and backups. | Thandi Khumalo - Backend Developer
Insufficient backup procedures | Backups may be incomplete or outdated | 5 | 2 | 10 | Medium | Schedule frequent automated backups with offsite storage. | Priya Singh - Network & Infrastructure Administrator
Cloud storage failure | Cloud provider outages could prevent access to company data | 4 | 2 | 8 | Medium | Use multi-region cloud backups and redundancy. | Lerato Mokoena - Chief Technology Officer
Accidental data deletion | Employees could mistakenly delete important information | 3 | 3 | 9 | Medium | Implement role-based access controls and backup restoration procedures. | Sipho Ndlovu - Technical Support Manager
Compromised IoT Devices | Sensors may have weak security and be hacked | 4 | 3 | 12 | High | Secure devices with strong authentication and network isolation. | Michael Jacobs - IoT Systems Engineer
Firmware vulnerabilities | Outdated firmware could containt security flaws | 3 | 3 | 9 | Medium | Regularly update device firmware and apply security patches. | Michael Jacobs - IoT Systems Engineer
Device connectivity loss | IoT devices may lose connection to the central platform | 3 | 3 | 9 | Medium | Implement network monitoring and automatic reconnection protocols. | Michael Jacobs - IoT Systems Engineer
Physical tampering | Devices in stores could be damaged or tampered with | 3 | 2 | 6 | Medium | Install devices in secure enclosures and monitor device activity. | Sipho Ndlovu - Technical Support Manager
Human Error | Employees may accidentally misconfigure systems | 3 | 4 | 12 | High | Implement change management procedures and system monitoring. | Natalie Ferreira - Finance & HR Manager
Lack of cybersecurity training | Staff may not recognize phishing or social engineering attacks | 3 | 4 | 12 | High | Provide regular employee security awareness training. | Kabelo Dlamini - Cybersecurity Specialist
Poor access control | Too many employees may have administrative privileges | 4 | 3 | 12 | High | Use role-based access control and least privilege policies. | Kabelo Dlamini - Cybersecurity Specialist
Mental health breakdown | Prolonged stress may result in decreased staff performance, increased operational errors, absenteeism, and disruption to business continuity. | 3 | 2 | 6 | Medium | Provide employee wellness support and workload management programs. | Natalie Ferreira - Finance & HR Manager
Office break ins | Theft of laptops or servers could compromise company data | 4 | 2 | 8 | Medium | Install alarm systems, surveillance cameras, and access control. | Daniel Naidoo - Chief Executive Officer
Fire | Fire could destroy servers, networking equipment and documents | 5 | 1 | 5 | Low | Install fire detection systems and fire suppression equipment. | Daniel Naidoo - Chief Executive Officer
Flooding or water damage | Water damage could destroy IT infrastructure | 4 | 1 | 4 | Low | Store equipment above ground level and install water detection sensors. | Daniel Naidoo - Chief Executive Officer
Unauthorized access to server room | If physical security is weak, anyone could access critical hardware | 5 | 2 | 10 | Medium | Implement keycard access control and surveillance monitoring. | Priya Singh - Network & Infrastructure Administrator
Natural disasters | Severe storms or flooding could disrupt operations | 5 | 1 | 5 | Low | Maintain offsite backups and disaster recovery locations. | Daniel Naidoo - Chief Executive Officer
Cloud provider outage | A major cloud outage could affect the analytics platform | 4 | 2 | 8 | Medium | Use multi-region cloud deployment and backup providers. | Lerato Mokoena - Chief Technology Officer
Supply chain disruptions | Delays in hardware replacement could extend downtime | 3 | 2 | 6 | Medium | Maintain spare hardware inventory and multiple suppliers. | Chris Botha - Sales & Client Relations Manager
ISP outages | Internet service provider issues could disconnect the company | 4 | 3 | 12 | High | Use redundant internet connections from different providers. | Priya Singh - Network & Infrastructure Administrator

## Scale
Risk Matrix
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T